## sheet1
No | Site ID | Site Name | Withdraw reason | HO date | Address | Approval Status | Infra MS reference Number | Operator | Latitude | Longitude | Pending Days | IMP Status as at | IMP Remark | 3G Marge cluster | Implementation project type | Implementation Scoop | RRU Count | New equipment required sector or Site | New equipment from | Cabinet | Cabinet + Batters | RRU/RFU | *MPT card | *BBP card | Fiber & Feeder from | Antenna | Vendor area | RNO engineer | Infra height ( m ) | Building Height ( m ) | Antenna Height (m) | Azimuth | Tilt | Civil operations | Comments
5 | MOWEL1 | Wellawaya |  | 44586.0004 | â€œVijithaâ€,Ella_Road,_Wellawaya. | Approved |  | Mobitel | 6.7354 | 81.1019 |  |  |  |  | LTE 1800 & L850 4th sector Installation | Antenna & RRU installation |  | MOWEL1F | SWAP existing SB antenna with TB antenna of 3rd secor Inastall 1*3928 RRU & 1*5903 RRU (3928 from COL437 removed & 5903 from BDELL1 removed) Direct existing TB antenna 3rd sector to 170 & New TB antenna 4th Sector to 250 UBBPd3 card from GMKUR2 | [6 empty] | 1*TB from ZTE BBE 2020 Removal | ZTE | Tiresh | 60 |  | 60 | 250 | 4 |  | Need to commission before 26th January 2022 as temporary installation due to VVIP visit Permeant installation can proceed after 28th January 2022